## Timeline
🚀 Day-1 Launch Schedule — Offline Translator v1.1
2026-04-21 (Tue) · Taipei 🇹🇼 · @mina0717 · All times PT (UTC-7) + TPE (UTC+8)
PT Time | TPE Time | Task | Platform | Status | Link / Notes | Done
— Day -1 — Final rehearsal
18:00 PT | 09:00 TPE+1 | Final build archive + upload to App Store Connect | App Store Connect | Pending | Requires Mac; see Mac測試與後續待辦.docx | ☐
20:00 PT | 11:00 TPE+1 | Schedule Product Hunt post (draft saved) | Product Hunt | Pending | Use PRESS_KIT.md quotes | ☐
22:00 PT | 13:00 TPE+1 | Draft all IG/Threads/X posts in Notion/Notes | Social | Pending | Pull from ig-cards/ + BLOG_POST | ☐
23:00 PT | 14:00 TPE+1 | Sleep (seriously) | — | Pending | Day-1 is long | ☐
— Day 0 — Launch day
00:01 PT | 15:01 TPE | Product Hunt post goes live | Product Hunt | Pending | https://producthunt.com/posts/TBD | ☐
00:05 PT | 15:05 TPE | Tweet launch thread (9 tweets) | X/Twitter | Pending | Include App Store link + landing page | ☐
00:10 PT | 15:10 TPE | Post IG carousel (5 cards) | Instagram | Pending | ig-cards/01-cover → 05-cta | ☐
00:15 PT | 15:15 TPE | Threads launch post | Threads | Pending | Reuse tweet #1 + IG card 01 | ☐
00:20 PT | 15:20 TPE | LinkedIn post (personal + detailed) | LinkedIn | Pending | Use blog post excerpt | ☐
00:30 PT | 15:30 TPE | Hacker News Show HN post | Hacker News | Pending | 'Show HN: Offline Translator — iOS, zero analytics' | ☐
01:00 PT | 16:00 TPE | Reddit r/iOS + r/privacy posts | Reddit | Pending | Subreddits: r/iOS, r/privacy, r/Taiwanese | ☐
02:00 PT | 17:00 TPE | First KPI check — PH rank, HN position | Monitoring | Pending | Screenshot for postmortem | ☐
04:00 PT | 19:00 TPE | Reply to PH comments (batch 1) | Product Hunt | Pending | Use FAQ from PRESS_KIT | ☐
06:00 PT | 21:00 TPE | Email press kit to 10 journalists | Press outreach | Pending | See press list in Notion | ☐
08:00 PT | 23:00 TPE | Check Apple Search Ads impressions | App Store | Pending | Verify keywords live | ☐
10:00 PT | 01:00 TPE+1 | Mid-day KPI snapshot | Monitoring | Pending | Downloads, PH rank, HN, GitHub stars | ☐
12:00 PT | 03:00 TPE+1 | Second X/Twitter post (follow-up) | X/Twitter | Pending | Highlight metric or testimonial | ☐
14:00 PT | 05:00 TPE+1 | Reply to Twitter/X replies (batch) | X/Twitter | Pending | Personal responses only | ☐
16:00 PT | 07:00 TPE+1 | Check Product Hunt — top 10? | Product Hunt | Pending | If top 5, push harder; if not, analyze | ☐
18:00 PT | 09:00 TPE+1 | LinkedIn follow-up + engagement | LinkedIn | Pending | Reply to comments, DMs | ☐
20:00 PT | 11:00 TPE+1 | Final Day-1 KPI tally + screenshot | Monitoring | Pending | Save to postmortem doc | ☐
22:00 PT | 13:00 TPE+1 | Thank-you post across all channels | Social | Pending | Template: '24h recap + gratitude' | ☐
23:59 PT | 14:59 TPE+1 | Day-1 closed. Sleep. | — | Pending | Day-2 follow-up tomorrow | ☐

## Platforms
📣 Platform Tracker
Platform | URL | Asset to use | KPI (Day 1 target) | Actual | Notes
Product Hunt | TBD post-launch | PRESS_KIT quotes + app icon | Top 10 daily · 200+ upvotes |  | Primary driver Day-1
X / Twitter | https://twitter.com/mina0717 | 9-tweet launch thread + IG card 01 | 50K impressions · 200 retweets |  | Use threadreaderapp pin
Instagram | https://instagram.com/mina0717 | ig-cards/01-05 carousel | 500 likes · 30 saves |  | Post at 15:00 TPE
Threads | https://threads.net/@mina0717 | Reuse tweet #1 + cover image | 200 likes |  | Link in bio update
LinkedIn | https://linkedin.com/in/TBD | Blog post excerpt + 01-hero.png | 20 reactions · 5 comments |  | Professional tone
Hacker News | https://news.ycombinator.com | 'Show HN: Offline Translator — iOS, zero data collection' | Front page · 50 points |  | Post 00:30 PT (HN prime time)
Reddit r/iOS | https://reddit.com/r/iOS | Title: 'I built an offline translator...' | 100 upvotes |  | Follow subreddit rules
Reddit r/privacy | https://reddit.com/r/privacy | Focus on zero-analytics angle | 50 upvotes |  | No self-promo flag
App Store | TBD post-approval | Screenshots 01-05 + what's new CN+EN | Featured in Utilities |  | Check search rank
GitHub | https://github.com/mina0717/offline-translator-ios | README + CHANGELOG + blog link | 100 stars Day-1 |  | Pin repo

## KPIs
📊 Day-1 KPI Tracker
Refresh every 2 hours. Formulas auto-calculate % of target.
Metric | Target | 02:00 PT | 10:00 PT | 20:00 PT | % of target
App Store downloads | 1000 | 0 | 0 | 0 | 0%
Product Hunt upvotes | 200 | 0 | 0 | 0 | 0%
Product Hunt rank (daily) | 10 | 0 | 0 | 0 | 0%
X impressions | 50000 | 0 | 0 | 0 | 0%
X retweets | 200 | 0 | 0 | 0 | 0%
X new followers | 100 | 0 | 0 | 0 | 0%
IG likes (carousel) | 500 | 0 | 0 | 0 | 0%
IG saves | 30 | 0 | 0 | 0 | 0%
HN front page time (min) | 120 | 0 | 0 | 0 | 0%
HN points | 50 | 0 | 0 | 0 | 0%
Reddit r/iOS upvotes | 100 | 0 | 0 | 0 | 0%
Reddit r/privacy upvotes | 50 | 0 | 0 | 0 | 0%
GitHub stars | 100 | 0 | 0 | 0 | 0%
Landing page visits | 5000 | 0 | 0 | 0 | 0%
Privacy policy clicks | 500 | 0 | 0 | 0 | 0%
AVG % of target |  |  |  |  | 0%

## Post-Launch
📅 Post-Launch — Day 2-7 Follow-ups
Day | Date | Task | Platform / Target | Done
Day 2 | 2026-04-22 | Write postmortem / 'Day 1 recap' blog post | Blog + X thread | ☐
Day 2 | 2026-04-22 | Reply to all Day-1 comments / DMs | All platforms | ☐
Day 2 | 2026-04-22 | Send thank-you DM to top 10 PH upvoters | Product Hunt | ☐
Day 3 | 2026-04-23 | Feature email campaign to newsletter list | Email | ☐
Day 3 | 2026-04-23 | Update landing page with 'As featured on...' badges | Landing page | ☐
Day 3 | 2026-04-23 | Publish user testimonials on Threads/X | Social | ☐
Day 4 | 2026-04-24 | Apple Search Ads: optimize keywords from Day-1 data | App Store | ☐
Day 4 | 2026-04-24 | Submit to /r/Taiwanese, /r/apple, /r/Japan (travelers) | Reddit | ☐
Day 5 | 2026-04-25 | Record 60-sec demo video for YouTube Shorts | YouTube | ☐
Day 5 | 2026-04-25 | Pitch to tech bloggers (Chinese + EN, 5 outlets) | Press outreach | ☐
Day 6 | 2026-04-26 | Review crash reports + user feedback | Dev | ☐
Day 6 | 2026-04-26 | Plan v1.2 feature list based on requests | Roadmap | ☐
Day 7 | 2026-04-27 | 'Week 1 numbers' transparency post | Blog + Threads | ☐
Day 7 | 2026-04-27 | Weekly retrospective — what worked, what didn't | Internal | ☐

## Templates
💬 Quick Response Templates
Copy + paste for rapid replies. Personalize before sending.
Scenario | Template
PH: 'How is it free?' | No servers, no analytics, no ads = no costs to cover. Translation runs on your iPhone. The only cost is my time, and shipping this felt worth it. 🫶
PH: 'Is it really offline?' | Yes — try airplane mode before opening. Apple's Translation framework (iOS 17.4+) does on-device translation after a one-time language-pack download. Source is MIT: https://github.com/mina0717/offline-translator-ios
X: Feature request reply | Love this idea — noting it for v1.2. If you're curious I keep the roadmap at [GitHub link]. Thanks for trying it 🙏
X: Bug report reply | Sorry about that — can you file it at https://github.com/mina0717/offline-translator-ios/issues? Include iOS version + device model. I'll ship a fix ASAP.
IG DM: 'How does it compare to Google Translate?' | Google Translate is more languages + better on literary text. Offline Translator wins on: privacy (zero data), offline-first, integrated OCR+voice+dictionary in one app. Different tradeoffs.
Reddit: skepticism reply | Fair question. The repo is MIT: [link]. Search for 'URLSession' in translation code — zero results. PrivacyInfo.xcprivacy declares empty arrays. Turn on airplane mode and it still works.
HN: technical detail | Built with SwiftUI + Apple Translation framework + Vision + SFSpeechRecognizer. MLKit as fallback for iOS 17.0-17.3. Dictionary is 170K words in Core Data. ~85 MB IPA.
Press: interview request | Thanks for reaching out! Happy to chat. Best over email (mina0717@proton.me) or Twitter DM. Press kit here: [PRESS_KIT.md link]. Available all week.
User: 'I love it, how can I support you?' | ⭐ star on GitHub, leave a review on the App Store, and tell one friend. That's genuinely all — there's no donate button and I don't want one.
Negative: 'Translation quality is weak' | Fair — Apple's Translation framework is tuned for everyday phrases, not literary/technical precision. For complex work, DeepL/Google are stronger. The app is meant for travel, messages, menus, quick lookups.